## Dashboard
Analytics Change Log Dashboard
Latest change date: 2026-10-15 ¦ Source: Change Log sheet
TOTAL CHANGES | PROPOSED | APPROVED | IMPLEMENTED | KPIs IMPACTED | DASHBOARDS IMPACTED
7 | 7 | 0 | 0 | 10 | 4

## Summary
Summary Tables (all values are formulas on the Change Log sheet; feeds the Dashboard charts)
Change Type | Count | Owner | Count
Feature Change | 1 | Product Analyst | 2
Event Change | 1 | Analytics Engineer | 1
Reward Mechanic Change | 1 | Backend Developer | 1
Withdrawal Method Change | 1 | Data Analyst | 2
Field Rename | 1 | BI Developer | 1
KPI Definition Change | 1
Dashboard Change | 1
Dashboard Impacted | Count | Status | Count
Executive Overview | 6 | Proposed | 7
Engagement | 4 | Approved | 0
Rewards | 2 | Implemented | 0
Withdrawals | 1 | Rejected | 0
KPI Impacted | Count | Check: type counts = total changes
Daily Reward Claims | 1 | OK
Daily Active Users | 1 | Impact counts use text matching on the ';'-separated cells; a new dashboard/KPI/owner name must be added to its table.
Task Completion Rate | 2
Completed Tasks | 2
Total Rewards | 2
Reward Reversal Rate | 1
Withdrawal Requests | 1
Withdrawal Success Rate | 1
Average Session Duration | 1
Total Session Time | 1

## Change Log
Date | Change | Old Definition | New Definition | Reason | Affected KPIs | Affected Dashboards | Affected Reports | Owner | Version | Status | Note: add new changes below the last row (dashboard reads rows 2-200).
2026-10-15 | Feature Change | Daily reward activity tracked as a general event | Track daily reward claim with a unique event ID | Improve event accuracy | Daily Reward Claims; Daily Active Users | Executive Overview; Engagement | Daily Engagement Report | Product Analyst | v1.1 | Proposed
2026-10-15 | Event Change | task_completed recorded when task is clicked | task_completed recorded only after successful validation | Prevent incorrect task completion counts | Task Completion Rate; Completed Tasks | Engagement; Rewards | Task Performance Report | Analytics Engineer | v1.1 | Proposed
2026-10-15 | Reward Mechanic Change | Reward amount stored without reward status | Record reward amount with pending approved reversed status | Track reward adjustments correctly | Total Rewards; Reward Reversal Rate | Rewards; Executive Overview | Reward Activity Report | Product Analyst | v1.1 | Proposed
2026-10-15 | Withdrawal Method Change | Withdrawal records contain a general method field | Use a standardized withdrawal_method field with approved values | Improve method-level reporting | Withdrawal Requests; Withdrawal Success Rate | Withdrawals; Executive Overview | Withdrawal Operations Report | Backend Developer | v1.1 | Proposed
2026-10-15 | Field Rename | session_minutes | session_duration_minutes | Make field meaning clearer | Average Session Duration; Total Session Time | Engagement; Executive Overview | Engagement Summary | Data Analyst | v1.1 | Proposed
2026-10-15 | KPI Definition Change | Task Completion Rate = task clicks divided by users | Task Completion Rate = validated completed tasks divided by eligible task starts | Measure actual completion rather than clicks | Task Completion Rate | Engagement; Executive Overview | KPI Performance Report | Data Analyst | v1.1 | Proposed
2026-10-15 | Dashboard Change | Executive Overview shows total task events only | Add completed tasks and validated reward activity | Improve decision-making | Completed Tasks; Total Rewards | Executive Overview | Executive Summary | BI Developer | v1.1 | Proposed